## Product Backlog
Nexus RAG — Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload PDF, TXT, and CSV documents so that the system can index them for search | MUST HAVE | - | Sakshi Patil | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a developer, I want documents to be chunked and converted to vector embeddings stored in ChromaDB | MUST HAVE | US-01 | Sakshi Patil | 3- Completed
Sprint 2 | Sprint 2 | US-03 | As a user, I want to ask natural language questions and receive semantically relevant answers from my documents | MUST HAVE | US-02 | Sakshi Patil | 3- Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want every AI answer to cite the exact source filename so I can verify the information | MUST HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 3 | Sprint 3 | US-05 | As a user, I want a corrective RAG mechanism that rewrites my query automatically if retrieval quality is poor | MUST HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 3 | Sprint 3 | US-06 | As a user, I want to register and log in so that my documents and history are private to my account | MUST HAVE | - | Sakshi Patil | 3- Completed
Sprint 3 | Sprint 3 | US-07 | As a user, I want AI-generated follow-up question suggestions after each answer | SHOULD HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 4 | Sprint 4 | US-08 | As a user, I want to see an answer confidence indicator (Verified / Not Found / Low) on each response | SHOULD HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 4 | Sprint 4 | US-09 | As a user, I want to generate an AI summary of each uploaded document with one click | SHOULD HAVE | US-01 | Sakshi Patil | 3- Completed
Sprint 4 | Sprint 4 | US-10 | As a user, I want to search and filter my conversation history by keyword | COULD HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 5 | Sprint 5 | US-11 | As a user, I want to copy any AI answer to clipboard with a single click | COULD HAVE | US-03 | Sakshi Patil | 3- Completed
Sprint 5 | Sprint 5 | US-12 | As a user, I want to delete all my documents and reset my index without losing my account | COULD HAVE | US-01 | Sakshi Patil | 3- Completed
Sprint 5 | Sprint 5 | US-13 | As an admin, I want the full system deployed on Reflex Cloud so users can access it online | MUST HAVE | US-01 | Sakshi Patil | 3- Completed

## Sprint Backlog
NOTE: Task sizing between 0.5–12 hours ¦ Nexus RAG Project
US ID | Task ID | Task Description | Start Date | End Date | Assignee | Activity | Status | Est. Hrs | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 — Document Ingestion & Indexing (2025-12-01 to 2025-12-14)
US-01 | T-01 | Set up project structure, install Reflex, LangChain, ChromaDB dependencies | 2025-12-01 | 2025-12-02 | Team | Setup | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Implement PDF loader using PyPDF and LangChain PyPDFLoader | 2025-12-02 | 2025-12-03 | Team | Build | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Implement TXT and CSV loaders with source metadata tagging | 2025-12-03 | 2025-12-04 | Team | Build | 3- Completed | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Implement RecursiveCharacterTextSplitter (600 chars, 100 overlap) | 2025-12-05 | 2025-12-06 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-05 | Integrate HuggingFace all-MiniLM-L6-v2 embedding model singleton | 2025-12-08 | 2025-12-09 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-06 | Build ChromaDB vectorstore creation and persistence logic | 2025-12-10 | 2025-12-11 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-02 | T-07 | Test document ingestion end-to-end with sample PDFs | 2025-12-12 | 2025-12-14 | Team | Testing | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
SPRINT 2 — RAG Pipeline & Chat Interface (2025-12-15 to 2025-12-28)
US-03 | T-08 | Implement MMR retrieval (top-4 chunks, lambda=0.6) | 2025-12-15 | 2025-12-16 | Team | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-09 | Build LLM relevance check step (YES/NO binary evaluation) | 2025-12-17 | 2025-12-18 | Team | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-10 | Implement automatic query rewriting when retrieval quality is low | 2025-12-19 | 2025-12-20 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-11 | Build source attribution — label each chunk with [Source N: filename] | 2025-12-22 | 2025-12-23 | Team | Coding | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-12 | Build Reflex chat UI with message bubbles, input box, send button | 2025-12-23 | 2025-12-24 | Team | Build | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
US-04 | T-13 | Add source chip components to display cited filenames per answer | 2025-12-26 | 2025-12-27 | Team | Build | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
US-03 | T-14 | Integration test: full query → retrieve → generate → display pipeline | 2025-12-28 | 2025-12-28 | Team | Testing | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
SPRINT 3 — Auth, Corrective RAG & Confidence (2025-12-29 to 2026-01-11)
US-06 | T-15 | Design user database schema (users.json with bcrypt hashed passwords) | 2025-12-29 | 2025-12-30 | Team | Design | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-16 | Implement create_user() and verify_user() with bcrypt hashing | 2025-12-31 | 2026-01-02 | Team | Coding | 3- Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-17 | Build Login page (/login) and Register page (/register) in Reflex | 2026-01-03 | 2026-01-04 | Team | Build | 3- Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-18 | Implement AuthState with rx.LocalStorage session persistence | 2026-01-05 | 2026-01-06 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-19 | Implement per-user isolated storage (data/, chroma_db/, history.json) | 2026-01-07 | 2026-01-08 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
US-05 | T-20 | Build corrective RAG loop with relevance evaluation and auto rewrite | 2026-01-09 | 2026-01-10 | Team | Coding | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
US-08 | T-21 | Implement confidence badge (high/not_found/low) on chat responses | 2026-01-11 | 2026-01-11 | Team | Build | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
SPRINT 4 — Features, Profile & Deployment (2026-01-12 to 2026-01-25)
US-07 | T-22 | Implement AI follow-up question suggestions after each answer | 2026-01-12 | 2026-01-13 | Team | Coding | 3- Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-23 | Implement per-document AI summary with 'Generate summary' button | 2026-01-13 | 2026-01-14 | Team | Coding | 3- Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-24 | Add live search/filter bar to History page | 2026-01-15 | 2026-01-16 | Team | Build | 3- Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-25 | Implement copy-to-clipboard button on all AI responses | 2026-01-17 | 2026-01-18 | Team | Build | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-26 | Add 'Delete all documents' feature with ChromaDB wipe | 2026-01-19 | 2026-01-20 | Team | Coding | 3- Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-27 | Build document stats dashboard (file size, segment count per file) | 2026-01-21 | 2026-01-22 | Team | Build | 3- Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US-13 | T-28 | Deploy to Reflex Cloud with GROQ_API_KEY and HF token env vars | 2026-01-23 | 2026-01-24 | Team | Deploy | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-13 | T-29 | UAT — test all pages, auth flow, upload, chat, history, profile | 2026-01-25 | 2026-01-25 | Team | Testing | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0

## Stand up Meeting
Nexus RAG — Daily Stand-up Log
Sprint | Day | Impediments / Blockers | Action Taken
Sprint 1 | Day 1 | None | Set up project: installed Reflex, LangChain, ChromaDB, HuggingFace sentence-transformers
Sprint 1 | Day 2 | Initial LangChain version conflicts with some dependencies | Resolved by pinning versions in requirements.txt; all packages installed cleanly
Sprint 1 | Day 3 | Difficulty selecting optimal chunk size for RAG accuracy | Tested 400, 600, 800 char chunks; chose 600 chars with 100 overlap for best balance
Sprint 1 | Day 4 | Embedding generation slow using free API quotas | Switched to local HuggingFace all-MiniLM-L6-v2 model — no API cost, runs on CPU
Sprint 1 | Day 5 | ChromaDB persistence not working across restarts | Fixed by using persist_directory and module-level singleton pattern
Sprint 2 | Day 1 | None | Implemented MMR retrieval with top-4 chunks and lambda=0.6 for diversity
Sprint 2 | Day 2 | LLM hallucinating answers not in documents | Set temperature=0, added 8 strict prompt rules, source-labeled chunks
Sprint 2 | Day 3 | Source citations missing for some document types | Fixed metadata tagging in loader.py — all file types now tag d.metadata['source']
Sprint 2 | Day 4 | Reflex WebSocket disconnecting after backend restart | Switched from asyncio.get_event_loop() to get_running_loop() — fixed
Sprint 2 | Day 5 | None | Completed chat UI with message bubbles, source chips, and typing indicator
Sprint 3 | Day 1 | None | Designed user DB schema; implemented bcrypt password hashing
Sprint 3 | Day 2 | rx.LocalStorage keyword argument error (default= not supported) | Fixed: use rx.LocalStorage('') not rx.LocalStorage(default=''); syntax corrected
Sprint 3 | Day 3 | Cross-state user_id lookup using async get_state() crashing sync handlers | Fixed: added current_user_id field to RAGState; set via set_current_user() on mount
Sprint 3 | Day 4 | None | Per-user isolated storage working; each user's docs fully private
Sprint 3 | Day 5 | None | Confidence badge and corrective query rewrite pipeline complete
Sprint 4 | Day 1 | None | Implemented AI follow-up suggestions and document summary features
Sprint 4 | Day 2 | reflex init interactive prompt causing Render build failure | Added --template blank flag to render build command — resolved
Sprint 4 | Day 3 | Python 3.14 incompatibility with Pydantic V1 on Render | Added .python-version file pinning Python 3.11.0 — resolved
Sprint 4 | Day 4 | None | Deployed successfully to Reflex Cloud with all env vars configured
Sprint 4 | Day 5 | None | UAT completed — all features tested and working end-to-end

## Retrospection
Nexus RAG — Sprint Retrospections
Sl # | Sprint # | Sprint Start | Sprint End | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 2025-12-01 | 2025-12-14 | Sakshi Patil | Write unit tests for each module as it is built | Manually testing only at the end of the sprint | Daily stand-up to surface blockers early | Added test cases for loader, vectorstore, and RAG pipeline
2 | 2 | 2025-12-15 | 2025-12-28 | Sakshi Patil | Use type hints and docstrings for all new functions | Hardcoding values in pipeline code | Using singletons for heavy model objects — saves restart time | Added type hints; moved all hardcoded values to config or env
3 | 3 | 2025-12-29 | 2026-01-11 | Sakshi Patil | Document every known bug and fix in the defect tracker in real time | Leaving LocalStorage and cross-state bugs until end of sprint | Per-user isolation pattern — keeps each user's data clean | All 3 auth bugs tracked and resolved same day they were found
4 | 4 | 2026-01-12 | 2026-01-25 | Sakshi Patil | Add more automated UAT scripts before cloud deployment | Deploying without verifying env vars are set in cloud dashboard | Clear README with step-by-step setup and troubleshooting guide | Pre-deployment checklist created; all env vars verified before deploy