## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Sakshi Patil | 2025-12-05 | ChromaDB vectorstore not persisting across restarts — data lost on every server stop | Sprint 1 | Sakshi Patil | Technical | Implemented module-level _vs singleton with persist_directory parameter in Chroma constructor | 2025-12-05 | Closed | Root cause: missing persist_directory arg
2 | Sakshi Patil | 2025-12-08 | HuggingFace embedding model reloading on every query — severe performance degradation | Sprint 1 | Sakshi Patil | Performance | Moved model to module-level _model=None singleton loaded once at startup in warmup thread | 2025-12-08 | Closed | Warmup thread pre-loads on startup
3 | Sakshi Patil | 2025-12-09 | No module named 'langchain_text_splitters' — import error on startup | Sprint 1 | Sakshi Patil | Configuration | Added langchain-text-splitters>=0.3.0 to requirements.txt and reinstalled dependencies | 2025-12-09 | Closed | Missing package in requirements
4 | Sakshi Patil | 2025-12-18 | LLM generating answers from training data not present in uploaded documents (hallucination) | Sprint 2 | Sakshi Patil | Logical | Set temperature=0; added 8 strict rules to prompt; labeled each chunk [Source N: filename] | 2025-12-19 | Closed | Hallucination eliminated at temperature=0
5 | Sakshi Patil | 2025-12-20 | Source citations missing for TXT and CSV file types — only PDF sources were shown | Sprint 2 | Sakshi Patil | Standards | Fixed loader.py — added d.metadata['source']=fname for all file types explicitly | 2025-12-20 | Closed | All 3 file types now properly tagged
6 | Sakshi Patil | 2025-12-22 | asyncio.get_event_loop() raises 'Event loop is closed' error after app restart | Sprint 2 | Sakshi Patil | Technical | Replaced get_event_loop() with asyncio.get_running_loop() in corrective_rag.py executor | 2025-12-22 | Closed | get_running_loop() always returns active loop
7 | Sakshi Patil | 2025-12-28 | Reflex WebSocket disconnects: 'Cannot connect to server: timeout' on first page load | Sprint 2 | Sakshi Patil | Deployment | Identified missing GROQ_API_KEY in cloud env; added keys via dashboard and restarted | 2025-12-28 | Closed | Always set env vars before deployment
8 | ]Sakshi Patil | 2025-12-31 | rx.LocalStorage TypeError: '__new__() got unexpected keyword argument default' | Sprint 3 | Sakshi Patil | Technical | Fixed syntax: use rx.LocalStorage('') not rx.LocalStorage(name='x', default=''); no kwargs | 2025-12-31 | Closed | Correct: rx.LocalStorage('default_value')
9 | Sakshi Patil | 2026-01-02 | AuthState get_state() returns coroutine — calling .user_id on it raises AttributeError | Sprint 3 | Sakshi Patil | Logical | Added current_user_id: str='' to RAGState; set via set_current_user(AuthState.user_id) on mount | 2026-01-02 | Closed | No async cross-state lookup needed
10 | Sakshi Patil | 2026-01-03 | Message and DocStat imported from wrong module — imported from auth_state instead of rag_state | Sprint 3 | Sakshi Patil | Standards | Corrected all page imports: Message, QAPair, DocStat imported from rag_state not auth_state | 2026-01-03 | Closed | States __init__.py re-exported all models
11 | Sakshi Patil | 2026-01-08 | Vectorstore stale after new upload — old index returned even after new documents processed | Sprint 3 | Sakshi Patil | Logical | Added reset_singleton() / _reset_vs(uid) call in handle_upload after _create_vs | 2026-01-08 | Closed | Cache invalidated on each new upload
12 | Sakshi Patil | 2026-01-15 | reflex init aborts on Render: 'Aborted!' due to interactive template selection prompt | Sprint 4 | Sakshi Patil | Deployment | Added --template blank flag to build command in render.yaml; non-interactive now | 2026-01-15 | Closed | Use: reflex init --template blank
13 | Sakshi Patil | 2026-01-16 | Python 3.14 incompatibility — Pydantic V1 core not compatible with Python 3.14 on Render | Sprint 4 | Sakshi Patil | Configuration | Added .python-version file containing '3.11.0' to pin Python version on Render | 2026-01-16 | Closed | Render reads .python-version to select Python
14 | Sakshi Patil | 2026-01-20 | Document summary shows 'Generating...' indefinitely if summarise_document raises exception | Sprint 4 | Sakshi Patil | Logical | Added try/except in summarise_doc; on error shows 'Could not summarise: [reason]' message | 2026-01-20 | Closed | Error message now shown instead of spinner
15 | Sakshi Patil | 2026-01-24 | History not restored on page refresh — check_existing_index not called on all protected pages | Sprint 4 | Sakshi Patil | Logical | Added check_existing_index() to on_mount of chat, upload, history, profile pages | 2026-01-24 | Closed | on_mount pattern standardized across all pages

## Sheet2
Logical
User Interface
Maintainability
Standards
Others